PUBLIC ART

POLICY AND PROCEDURES

Updated:

September 2003

Table of Contents

INTRODUCTION	1

What is Public Art?	1

PART ONE CITY-FUNDED PUBLIC ART	2

Public Art Funding - Percent for Art Requirement	2

Summary of the Process	2

Funding Policies	3

Funding Procedures	3

Project Manager's Role	4

Generating Ideas For Public Art in Capital Projects	6

Methods of Selecting Public Art	8

Evaluating And Selecting Public Art	9

Design Review/Public Hearings	10

Artist Compensation	12

Public Art Installation	12

Maintenance and Repair	13

Legal Issues	15

Dedication of Artwork	16

PART TWO PRIVATELY FUNDED ART IN PUBLIC PLACES	17

Submittal Of A Proposal	17

Evaluation Of A Proposal	17

Approval of a Proposal	18

Contract Preparation	19

Issuing of Permits	19

Labeling of Artwork	19

Final Acceptance	19

Dedication of Artwork	20

PART THREE PUBLIC ART IN PRIVATE DEVELOPMENT	21

Placement of Public Art on Private Property	21

Public Art Donated to the City by a Private Developer	22

Payment of Art In-Lieu Fee	23

Certificate of Occupancy	23

Ownership of Public Art	24

Removal or Alteration of Public Art	24

Use of the Public Art In-Lieu Funds	24

APPENDICES

Appendix A:  Resolution No. 6811 Adopting a Visual Arts in Public Places Program

Appendix B:  Sample RFP

Appendix C:  Guidelines for Public Art/Public Art Selection Criteria & Rating Sheet

Appendix D:  Sample Architectural Review Commission Agenda Report

Appendix E:  Sample Agreement to Design and Install Public Art

Appendix F:  Public Art Final Acceptance Letter

Appendix G:  Public Art Maintenance Record

Appendix H:  Dedication Ceremony

Appendix I:  Application Privately Funded Art on City-owned Property

Appendix J:  Resolution No. 8965 Adopting a City Donation Acceptance Policy

Appendix K:  Ordinance No. 1372 Public Art in Private Development

Appendix L:  Planning Application/Public Art Proposal

Appendix M:  Public Art Maintenance Covenant

Appendix N:  Resources for Private Developers

Appendix O:  Miscellaneous Background Material/Staff Reports, etc.

# INTRODUCTION

## What is Public Art?

Public Art develops from the engagement of an artist with public space.  Within the realm of creating public art, artists encounter people, history, and process.  The resulting artwork represents the diverse response to those factors by individual artists, leaving the question, “what is public art?”

It's easier to describe what isn't public art.  Fancy "off-the-shelf" benches, fountains, and trash receptacles; upgraded tile, paving, or other conventional architectural finishes and ornamentation; standard landscaping; architectural lighting; and other similar treatments which do not involve original, creative work by an individual or group are not normally considered public art.

For example, purchasing a pre-fabricated fountain and installing it in a park would be landscaping but not public art, since the piece is a stock item and its design does not necessarily involve an original or creative effort.  However, if the fountain included an original ceramic or bronze sculpture, tile mosaic, or other original or creative feature it could be considered public art.  The artwork doesn't necessarily have to be one-of-a-kind, or designed only for that location -- it could be one of a limited series of castings (in the case of sculpture) that has been thoughtfully integrated with a project.

The boundary between architectural ornamentation and art is not always clear.  For example, in decorating a blank wall of a parking garage with a series of metal screeds and painted wall panels, the architect's effort might be considered public "art" if it were an original work, went beyond typical or stock architectural treatment, and met the city's public art guidelines.

Funding for public art can come about in a number of different ways and currently includes the following three options:

  - City Funded Public Art.  Each year the City of San Luis Obispo sets aside one percent (1%) of the estimated cost of eligible projects in its Capital Improvement Plan for public art.

  - Privately Funded Art in Public Places.  Private citizens may donate public art to the City for personal reasons.

  - Public Art in Private Development.  The City requires private developers to include public art in their projects valued at one-half of one percent (.5%) of the cost of construction over $100,000.  Optionally, developers may contribute an amount equal to the value of the required art to the City’s art-in-lieu account or donate a comparably valued piece of art to the City.

There are different procedures to be followed for each source of public art.  Accordingly, this manual is divided into separate sections that cover each of these processes.

# PART ONE
CITY-FUNDED PUBLIC ART

## Public Art Funding - Percent for Art Requirement

In May 1990, the City Council established and funded a public art program.  The Council determined that one percent (1%) of the estimated construction cost of eligible projects in the Capital Improvement Plan should be set aside for public art. (See enabling legislation, Appendix A)

## Summary of the Process

- The Finance Department includes an art funding component in each Financial Plan budget request equal to 1% of the construction component for all eligible projects.

- A committee comprised of City staff, currently the Capital Improvement Plan Committee, determines which capital projects will be recommended for public art, based on available funding and suitability of project.  The committee also recommends funding levels for each project.

- Council approves committee’s recommendations for public art in certain capital projects.

- Art is incorporated into preliminary project studies and design for recommended projects.

- Project manager solicits artist's proposals.

- Project manager works with the Public Art Coordinator to appoint an art jury.

- Artist/artwork is selected by jury.

- Proposed artwork is reviewed by Public Works staff, as appropriate.

- Proposed artwork is reviewed by the Cultural Heritage Committee, the Parks and Recreation Commission and/or the Mass Transportation Committee, as appropriate.

- Architectural Review Commission (ARC) approves artwork and forwards recommendation to City Council.

- City Council approves artwork.

- Project manager prepares public art contract.

- Project manager secures planning/construction permits and works with artist to fabricate artwork.

- Artwork is installed.

- Project manager and Public Art Coordinator inspect artwork and compile maintenance information.

## Funding Policies

The following administrative policies have been developed to effectively manage the City-funded public art program:

1.	Eligible Projects.  All Capital Improvement Plan projects are considered eligible for public art, and are expected to contribute to the City’s public art fund in an amount equal to one percent (1%) of the project's construction cost, unless the project is exempt.  Exemptions include:

- Utility projects, such as sewer or water system improvements.

- Underground projects, such as new storm drains, storage tanks and similar items.

- Public art projects themselves.

- The portion of any project funded by grants from outside agencies.

2.	Public Art Account.  A Public Art Account is maintained by the Department of Finance to fund public art projects.  As part of the Financial Plan process, every two years, an amount equal to one percent (1%) of the construction component of all eligible projects is placed in this account. Funding is then transferred by Finance staff to either a public art phase of a capital project account or to a specific public art project account once the Council determines which capital projects are appropriate for public art.

## Funding Procedures

The following procedures are followed by City staff to set up funding for public art projects.

1.	Identify Capital Projects. Departments normally submit Capital Improvement Plan Requests for the construction of projects during the regular budget cycle. As part of those submittals, the Finance Department includes a public art funding component equal to 1% of all eligible project’s construction costs.

2.	Public Art Account.  Public Art funds identified in a Capital Improvement Plan and approved by Council are then set aside in a "Public Art Account".

3.	Allocation of Public Art Funds to Projects.  Following approval of the two-year Financial Plan, the City's Capital Improvement Plan (CIP) Review Committee meets to determine which capital projects are most appropriate for the inclusion of public art, as well as an appropriate level of funding for each project.  The following criteria is used to identify projects suitable for public art:

- Project should have high public visibility and use.

- Project should lend itself to the inclusion of public art.

- Project should be public art ready, meaning the project should be nearing the design phase or near or under construction and will be completed within the two year CIP.

- The number of projects should be limited in order to focus staff efforts and result in meaningful pieces of public art.

The Public Art Coordinator forwards the Committee's recommendations to the Council for approval.

4.	Transfer of Funds to Project Budgets.  Upon Council approval of recommended public art allocations, the Finance Department transfers funding from the Public Art Account to the public art line item in the designated project budget.

5.	Staff Reports to City Council.  Staff reports submitted to the City Council or to the CAO to request approval to solicit bids or proposals for capital projects state whether public art has been designated as part of the project scope.  If the project has been approved for public art, the discussion includes a suggested art theme, how proposals will be solicited, and the estimated cost of the public art project.  This information is included in the staff report under a separate sub-heading at the end of the "DISCUSSION" section entitled “Public Art”.

## Project Manager's Role

Project managers are assigned to all capital projects.  They are responsible for getting projects built -- from developing the project concept to ribbon cutting.  Specifically relating to public art, the project manager is responsible for the following:

1.	Eligibility and funding.  Making sure that for each capital project, s/he has answers to the following:

a.	Is the project designated for public art?

b.	If so, has the funding been transferred to the project budget?

c.	Has sufficient funding been set aside from the allocation for artist pre-selection stipends, plaques, and dedication ceremonies (usually $1000).

2.	Planning and design.  Although project managers are not expected to design the artwork, they are expected to recognize and plan for the possibilities.  The Public Art Coordinator provides assistance with this phase of the project, if necessary.  Steps would typically include:

a.	Identifying possible locations in a capital project for public art.  The project designer, an artist or representatives from local arts organizations may help suggest artwork sites.

b.	Suggesting the general type of public art possible, for example, ground- or wall-mounted sculptures, murals, landscape art, special architectural features, such as windows, benches or railings, or other possibilities.

c.	Determining whether the approved budget is adequate for the proposed art concept. Some projects may warrant larger public art expenditures.  For example, important public buildings like a performing arts center or City Hall expansion may offer special opportunities for public art and a decision may be made to request Council augmentation of the approved budget.

d.	Designing the capital project to accommodate public art.  The location of the artwork should enhance the project's overall appearance, and be publicly visible or accessible. Whenever possible, the artwork should be a part of the actual project itself.

3.	Selection of Artist and Artwork.  Like other consultants or contractors who work on capital projects, artists work under contract with the City.  The project manager administers the selection and contracting process, with assistance from the Public Art Coordinator, as needed.  Tasks include:

a.	Determining the best method for selecting an artist (See Methods of Selecting Public Art).

b.	Arranging for proposals and artists to be evaluated by a selection committee or "jury".

c.	Providing the Public Works Director or his/her designee the opportunity to review the design proposal for impacts of proposed placement or maintenance.

d	After jury acceptance of a proposal, assuring that the Architectural Review Commission (ARC) and other appropriate advisory body review has occurred regarding whether the proposed art piece is consistent with the City’s Guidelines for Public Art (Appendix C).

e.	Preparing an agenda report and taking the selected artist’s design to the Council for approval.

f.	Preparing contract documents.

4.	On-going review.  The project manager takes steps to insure a smooth construction process by:

a.	Processing invoices and other pay requests.

b.	Monitoring and inspecting work progress to insure a quality project.

c.	Following up to insure that the artwork meets all code requirements and permit conditions.

5.	Final Inspection and Acceptance.  The final steps for the project manager include:

a.	Arranging for final inspection of artwork by appropriate City staff.

b.	Verifying in writing that the artwork has been completed per contract.

c.	Arranging for a plaque acknowledging the artwork and artist.

d	Arranging for City Council and/or public reception/dedication for the project and the artwork.

## Generating Ideas For Public Art in Capital Projects

A project manager is not expected to be an artist or to single-handedly create public art. S/he is expected, however, to be the catalyst, and to take the necessary steps to make it happen.  Again, consulting with local artists or representatives from the local arts organizations may be helpful.

1.	Getting Started.  A project manager influences how a project looks and works.  So, too, with public art.  Initially, his/her key role is to define the possibilities for art.  To do this, s/he should:

a.	Know the site.  Contact the County Historical Museum, Cultural Heritage Committee, the San Luis Obispo County Arts Council, local historians, the Public Art Coordinator or other City staff to understand the site's background.  For example, what is the site's cultural or historic significance?  How is it (or how could it be) related to other public spaces or facilities?  How has it changed over time?  Does it have environmental features that might be repeated in the artwork?  Could the art become a part of the architectural fabric of the building?

b.	Be aware of site context.  A historic neighborhood or building, natural feature, or cultural pattern (e.g. Chinatown, Government Center, Mission Plaza, etc.) can strongly influence the type of art selected.

c. 	Look for design opportunities.  Most projects will not automatically present locations for art -- the opportunities usually have to be created.  This means thinking about how art could be included early in the project study and design phases, not after the construction drawings are done.  Some creative approaches to incorporating art in project designs include:

- A city building that incorporates bas-relief sculpture or mosaic tile into its exterior design, and changeable exhibit space inside.

- A parking lot that includes a unique seating area or sculpture.

- A bikeway with a series of decorative panels inset into the paving.

- A bridge with a gateway arch, mural, or water feature.

2.	Generating ideas.  The possibilities are numerous.  They grow out of the site's characteristics, context, functional needs, and the project’s design.  It starts when the project manager (in collaboration with artists, arts organizations or other staff) generates some ideas -- keeping them loose and very open-ended at first.  For example:

a.	Public Buildings:

- Provide interior wall space or display cases in prominent interior locations for the changeable display of public art, possibly from school or community groups; or works on loan from artists or arts organizations.

- Emphasize permanent artwork at building entries, exterior patios or courtyards, or any visually prominent location used by the public.  Consider using rich, architectural materials that integrate art with the building, such as the tile mosaic of Old Mission life at the rear entrance to City Hall.

b. 	Parks, plazas, playgrounds:

- Sculpture, entry gates, specially designed walkways, murals, landscape art, fountains, and artfully designed street furniture, signage, trash receptacles, bike lockers, bike racks and bandstands are just a few possibilities.

c. 	Streets, alleys, median planters, sidewalks, trails, bikeways, public transportation and parking facilities:

- These locations offer some of the best opportunities for public art.  They are highly visible and accessible.  And due to the large expanses of paving, they can often benefit from the visual interest and variety that public art can provide.  Linear or repeating artworks can be used, for example, to unify a bikeway plan and provide orientation stations along routes.

d.	Miscellaneous Projects.

- Bridges, creek improvements, above ground utility stations, and other special facilities also present public art opportunities where they have good public visibility.  Creek projects, in particular, should include art that enhances the creek’s natural beauty and ecological diversity.

3.	Getting Help.  Public art is one more item that project managers need to consider in getting projects built.  There are resources both inside and outside City Hall to help with this task.  For example:

a.	The Public Art Coordinator can explain the public art program requirements, will help facilitate the review of art projects through the various public approvals, including jury selection, public relations and Council approval, and will provide a list of potential artists to receive the request for proposals;

b.	Finance staff can advise you on funding strategies and requirements;

c.	The San Luis Obispo County Arts Council assists the City by providing expert technical advice and commentary on public art, and serves as a liaison between the City and the art community;

d.	The San Luis Obispo County Arts Council Directory, located on their web site (www.sloartscouncil.org) is also a good source for ideas and finding artists.

## Methods of Selecting Public Art

Since public art is often such a prominent visual feature, it is important that each artwork be thought through carefully.  Early public participation is a key part of the process.  Another key aspect is involving the artist in the overall project design phase early on so that the work of art is well integrated with the site and/or buildings.

1.	Developing Artwork Parameters.  Before a project manager is ready to hire an artist, s/he should set some general parameters to help guide artist selection.  Based on knowledge of the site and the project's design possibilities, s/he should identify a number of possible locations and general types of art that would work for the project.  The project manager should then request feedback on these ideas from other staff, or the San Luis Obispo County Arts Council, as mentioned earlier.  (See previous section, Generating Ideas for Public Art in Capital Projects.)

2.	Selection Strategies.  Typically, an artist is selected in one of the following manners:

a.	Requests for Proposals.  A Request For Proposals (RFP) is the most common method used for selecting an artist.  Public notice follows standard purchasing procedures.  In addition to legal notice in the papers, the project manager should contact the Public Art Coordinator to obtain a current list of potential artists and art organizations to be notified. An example of the standard public art RFP is located in Appendix B.

b.	Sole Source.  This approach reflects the fact that public art is fundamentally different from most other types of public works.  With art, we are looking for an individual expression or unique idea -- not price comparisons for one plan or idea.  In some cases, the Council or project manager may have a specific artist or type of art in mind, and may choose to request a proposal from an individual artist without going through competitive selection.  This approach requires Council approval and needs to be clearly justified in writing by the project manager, i.e. why competitive selection is not needed or desirable, and how sole sourcing will better meet the City's objectives for the project.

c.	Acquisition.  Acquisition of an art piece that has already been completed by an artist may be appropriate in some very rare circumstances.  The purchase price and the cost of installation comes from the percent-for-art budget.  Council approval is required before this process may be used.

3.	Policy statement on artist recruitment.

One of the City's goals is to promote the involvement of local artists and citizens in the public art program although project managers should seek artists from throughout the state of California.  In juried art competitions, all other factors being equal, local artists will be given preference.

## Evaluating And Selecting Public Art

In cities throughout the U.S. there has been growing support for public art.  However, some projects have been widely criticized as being "plop art" -- elements simply "plopped" down without sensitivity to the site or to the people who use the space.  Understanding what to look for and integrating artists in the early stages of a project can help to avoid "plop art."

1.	Selecting an Art Jury.  The majority of City public art projects will use the Request for Proposals (RFP) selection method. Art juries help staff evaluate the proposals received and make a final selection to proceed through the remainder of the approval process.  The preferred approach is to create a five to six member jury for a project.  In some cases, a slightly larger jury may be necessary to accommodate all the parties impacted by the artwork.  Jury composition will vary depending on the type of art project but should include a selection of the following, as appropriate:

- An Arts Council Member

- At least two professional artists in an appropriate discipline (i.e. painters or muralists for a mural)

- A neighbor or representative of a neighborhood association when are impacts a neighborhood.

- A for-profit or non-profit business representative, preferably one whose business will be impacted by the project

- An educator/historian, or someone aware of the historical implications of the artwork in the community

- As appropriate, a member of the Downtown Association

- As appropriate, a member of the Parks and Recreation Commission, the Cultural Heritage Committee or the Mass Transportation Committee.

The Public Art Coordinator and the San Luis Obispo County Arts Council can assist the project manager in contacting appropriate artists and members of the Arts Council.  The Public Art Coordinator has a current list of prospective jurors who have indicated a desire to serve on an art jury.

2.  The Jury Process

a.	Initial review.  Once a jury has been selected, the project manager schedules a jury review. Two weeks prior to the official jury review, the project manager distributes to each juror a binder with copies of all proposals, the Guidelines for Public Art and a Public Art Selection Criteria and Rating Sheet (Appendix C) for each proposal.  (Proposal contents are specified in the RFP.)  A “blind selection” process is used during this part of the review.

b.	Initial rating.  At the jury review, the project manager presents each proposal and examples of submitting artists’ work.  After discussion, jurors rate each proposal on a scale from “0” to “8”.  “Pluses” and “minuses” may be used.  A “0-2” rating means the work should not be considered further.

c.	Initial ranking.  Once all jurors have had an opportunity to rate the proposals, the project manager provides the jurors with a summary of the preliminary ratings.  Following discussion of the preliminary ratings, the jury develops an initial ranking of proposals. Note:  The jury ultimately has the final say in the selection, regardless of the result of the rankings. Depending upon the quality of the proposals and number of submittals, a “short list” of three (3) to four (4) artists will then be asked to prepare a more extensive representation of the proposed artwork to present it to the jury at a second review.

d.	Artist stipend for proposal design.  Sufficient funding is held back from the available project budget to allow stipends to be paid to the selected finalists as a partial compensation for the cost of the design presentation (often a “maquette” or small scale model) for the interview process.  Stipends will be a maximum of $150 per artist.

e.	Final Selection.  Following artist interviews and design review of the top proposals, the jury selects a final design that then proceeds forward for review by the appropriate Commissions/Committees, the Architectural Review Commission and final approval by the City Council.

## Design Review/Public Hearings

1.	Public Works Department Review.  Prior to beginning the initial planning review, the project manager arranges for the project to be reviewed by appropriate staff in the Public Works Department.  The purpose of this review is to uncover any significant maintenance issues that may arise out of the proposed placement of the art or the choice of materials for the artwork.  The artist should also be present at this meeting to answer questions or provide additional input.  If the artwork is part of a larger construction project, it may be valuable to have the project contractor present, as well.

2.	Planning Review

a.	Review Steps.  It is the project manager's responsibility to initiate planning applications, submit plans, and ensure that capital projects go through the required public hearings.  The standard City policies apply to legal notice requirements, appeals, and environmental review.  For more information on these details, contact Community Development Department staff.  Typically, public art as part of capital projects follows these public review steps:

- environmental review (typically Categorically Exempt and not required if public art proposal is in the interior of a structure)

- review by the Architectural Review Commission

- final approval by the City Council

(1)	In special cases, the artwork will also require review by:

- Planning Commission (if the overall project requires a use permit)

- Parks and Recreation Commission (if in a City park)

- Cultural Heritage Committee (if in Mission Plaza or other designated historical area)

(2)	Art projects deemed "minor or incidental" can be approved by the Community Development Director, subject to the usual public notice requirements.

b.	Concurrent Review.  It is preferable for the artwork to be designed, reviewed, and approved concurrently with the capital project.  This approach:  1) allows the artwork to be designed as an integral part of the overall project; 2) allows the design, fabrication, and installation of the artwork under a single contract; and 3) is usually easier and more efficient in terms of staff time and public review.

c.	Separate Review.  Sometimes, for reasons of design, funding or timing, it is necessary to plan the public art after the main project design is completed.  Although the general location and type of artwork should be decided during the project planning stage, the actual design and implementation is then handled separately from the main project bidding and construction.  The best approach depends on the particular project, and the project manager needs to discuss alternatives with department management and the Public Art Coordinator.

- Architectural Review Commission and Other Commission Review.  It is important for a project manager to understand the role of the Architectural Review Commission (ARC) and other Commissions/Committees in reviewing public art.  The art jury has already selected the artistic design, and future review must respect the integrity of that design.  The ARC is charged with insuring that the proposed artwork meets the City’s Guidelines for Public Art (See Appendix C) and that it is appropriate for the proposed location.  Minor adjustments could be suggested, for example, to make the location fit better.  However, the ARC or any other City Committee or Commission should not become involved with redesigning the actual artwork.  Appendix D contains a template and an example of a public art staff report for an ARC meeting.

- Time Frame.  Be sure to plan ahead to keep the review process moving smoothly.  In some instances, it may take 4-6 weeks to be placed on a Commission/Committee agenda once an application is received (i.e. the Architectural Review Commission).

## Artist Compensation

1.	Methods of Payment.  Artists can be paid on an hourly basis, with fixed payments tied to a performance schedule, by lump sum, or on some other basis, similar to other types of consultants.  Whatever the approach, payments should be tied to a clearly defined and agreed upon schedule of performance.  It is also customary to pay a retainer fee of 20-25% of the total contract price upon awarding the contract.  Any other terms or special conditions, such as a liquidated damages clause, unforeseen costs or delays, and other provisions are negotiated on a case-by-case basis as necessary.  A modified version of the City’s standard contract should be used.  See Appendix E for a sample artist contract agreement.

2.	Typical Payment Schedule.  A typical artist's payment schedule will relate compensation to the value of work received, as in the following example:

Award of Contract	25%

Mid-point of Contract	50% **

Acceptance of Completion	25%

**	Depending on the type of art involved, different milestones can be set to establish when mid-construction payments should be made, i.e., for a sculpture, when artwork goes to the foundry could be one phase, completion of foundry work could be another.  If an extensive construction design plan is needed, completion of that plan could be a payment milestone.

## Public Art Installation

Like most other construction projects, public art requires plans and specifications.  Although these may vary in terms of detail and complexity, even the simplest art project requires plans and specifications, either included with a larger bid document being issued for the entire capital project (if the construction contractor is responsible for installation) or a separate bid (if the artwork is a free-standing project and being installed by someone other than the artist.)

1.	Plans and Specifications - What's needed?  Plans for public art projects require much of the same information as other types of new developments.  Depending on the type of public art, the following information is typically:

- Site Plan

- Grading Plan (if appropriate)

- Elevation/section drawings (if appropriate)

- Design, attachment, and/or fabrication details

- Structural Calculations

- Material and performance specifications

- Maintenance program

Each project is different, and the project manager will need to decide how much, and what type of information is needed to successfully fabricate and install the artwork.

2.	Plan Check, Permit and Inspections

a.	No Building Permit Required.  Most types of freestanding public art are treated as structures in the Uniform Building Code, and require a construction permit; however, the City is not legally required to get a building permit for its own capital projects.

b.	Inspections.  Any public art project that poses structural safety concerns should be reviewed by the Chief Building Official for safety.  Inspections are required to insure that the project is built as approved.

(1)	For small projects, like small sculptures, murals, or similar projects where structural safety is not a concern, one building inspection is usually sufficient upon completion.  The Public Art Coordinator also does a final inspection when the project is complete.

(2)	For larger or more complex projects, several inspections may be needed.  It is the project manager's duty to call Building and Planning staff to set up the inspections.  If the inspector finds problems or changes from approved plans, s/he sends a correction list to the project manager within 48 hours of the inspection.  The project manager then needs to coordinate with the artist, architect, and other staff members to resolve the "punchlist" items before the City finally "accepts" the artwork and makes final payment for the work.

3.	Final Acceptance.  All new public art projects, whether freestanding or part of a larger capital project, require a final acceptance by the Public Art Coordinator, acting on behalf of the City.  After the art project has been signed off by all inspectors, the project manager prepares a letter formally accepting the artwork.  The letter documents completion of the artwork, triggers artist and/or contractor payments, and allows the City to express thanks and congratulations to key participants.  The letter is signed by the Public Art Coordinator and the project manager and addressed to the Community Development Director, with copies to the CAO, project architect or engineer, project artist and contractor.  (See Attachment F for sample acceptance letter.)

## Maintenance and Repair

Like most City facilities, public art requires maintenance and occasional repairs.  Although the City's guidelines encourage artworks requiring "little or no maintenance", artworks will vary in the amount of maintenance required, resistance to vandalism, and ease of repair.

1.	Maintenance Record Form.  It is essential that the artist and the City be clear about maintenance expectations up front.  Prior to final acceptance of the artwork, the Public Art Coordinator insures that the artist has completed a Maintenance Record Form.  A sample form is provided in Attachment G.  The original copy of the form is kept by the Public Art Coordinator and a copy is forwarded to the Parks Division of the Public Works Department.

2.	Maintenance Responsibility.  The Public Works Department is responsible for maintaining City facilities, and this includes all City-owned or City-sponsored public art.  Temporary artworks owned by others but exhibited in City buildings or on City-owned land are the responsibility of the owner, unless other arrangements are made by prior agreement with the City.  A list that identifies which Public Works Department division is responsible for the maintenance of a particular piece of public art is available from the City’s Public Art Coordinator.

3.	Maintenance Cost.  The cost of routine maintenance is included in the Public Works Department budget.  For this reason, it is important that Public Works staff be allowed to evaluate any public art prior to it going through the planning review process.  During that review, changes to the art project may be made that do not compromise the integrity of the artwork itself, but do reduce maintenance costs.

4.	Types of Maintenance.  City crews are responsible for:

a.	Routine Maintenance. Such maintenance includes trash and graffiti removal, cleaning, waxing, minor landscaping, replacing light bulbs, and mechanical activities like tightening, adjusting, and oiling.  Frequency will vary by type of artwork, but bi-weekly or monthly checks by maintenance staff during the normal course of their rounds would be typical.

b.	Cyclical Maintenance.  Cyclical maintenance is done at regular, but much less frequent intervals.  It involves more extensive treatment such as disassembly, inspection, and surface applications of protective coatings (e.g. repainting). Because this work could significantly affect the appearance and longevity of the artwork, it may require special knowledge or skills.  Before proceeding with the work, staff should either:

(1)	Consult the artwork's Maintenance Record Form for specific procedures, or

(2)	If a Maintenance Record Form is not on file, consult the artist or other competent art professional on use of cleaning compounds, paints, solvents, and surface coatings.

c.	Repair and Restoration.  This involves the treatment of damaged or deteriorated artworks to return them to as close to their original appearance as possible.  Extreme care must be used to maintain the artistic integrity of the artwork.  The repairs must preserve the artist's intent in both design and materials.  In many cases, such repairs require the involvement of the original artist, or if that is not possible, an art conservator trained in art restoration.  Again, the artwork's Maintenance Record Form, prepared by the artist prior to final City acceptance of the artwork, gives some guidance on this issue. The City has an ethical, if not a legal responsibility to maintain the artistic integrity of an artwork (Calif. Art Preservation Act, Cal. Civ. Code 987 (West Supp. 1985)).  Improper maintenance and repair methods can damage valuable artworks, and may trigger legal challenges by the artist.

## Legal Issues

1.	Ownership.  In most cases, the City will own public art installed in connection with capital projects -- but not always.  For example:

a.	City-funded Public Art.  Under the terms of the City’s contract with the artist, all City-funded art installed on City property is owned by the City upon its completion.

b.	Jointly Funded Public Art.  Sometimes private funding may be used to augment City funds for public art on City property.  Due to the joint sponsorship, an "art agreement" is necessary between the City and other government agencies or private sponsors that clarifies mutual roles, responsibilities, funding levels, and other terms.

2.	Insurance Requirements

a.	During Fabrication of Artwork.  Because of the uniqueness of each piece of public art, the City’s Risk Manager needs to be consulted to determine the appropriate type and level of insurance that must be carried by an artist during the time the artwork is being fabricated and installed.  As a service to the artist, the City currently offers an insurance policy that can be purchased through the City.  Cost of the insurance varies depending on the value and scope of the artwork.  The artist should be directed to the Risk Manager for a cost estimate and to complete appropriate paperwork.

b.	Upon Acceptance by City.  Once a permanent artwork is formally accepted, the City assumes responsibility and liability for it.

3.	Relocation, Alteration or Removal

a.	Reasons for Relocation, Alteration or Removal.  From time to time, permanent City-owned artworks may need to be relocated, altered, or removed from public display.  Reasons for such changes could be as follows:

(1)	when significant changes occur in the design or function of the site or facility where the artwork is located;

(2)	to avoid damage to the artwork, e.g. during construction activities or as a result of vandalism, war or civil unrest, natural disasters, and environmental pollution;

(3)	to allow major repairs or restoration that could not be effectively done in place;

(4)	to improve public health, safety or welfare; or

(5)	to promote the public interest and the City's Visual Arts in Public Places program goals.

b.	Approval of Relocation, Alteration or Removal.  As necessary as removal or relocation may seem, it should be undertaken only after careful consideration and only as a last resort.  Artworks are usually created for a specific location, and changes may not be consistent with either the City's or the artist's original intent.  Moreover, California, New York, and Massachusetts have enacted laws establishing artists' "moral right" to protection of their work against unauthorized alteration or destruction.  To ensure that all parties' needs and rights are considered, City Council approval must be secured for the relocation, alteration, or removal of permanent, city-owned artworks.

c.	Contract Language on Relocation, Alteration or Removal.  Project managers must make sure that:

(1)	The artist's contract clearly acknowledges the City's rights to relocate, alter or remove the artwork, with or without special conditions requiring written notice to the artist, prior artist permission, arbitration in the event of a dispute, or other provisions;

(2)	The city has the permanent addresses and phone numbers of the artist and at least one other responsible party who can be contacted regarding relocation, alteration or removal.  It is the responsibility of the artist to keep this information current.

## Dedication of Artwork

Once installation of the artwork is complete, the Project Manager, with assistance from the Public Art Coordinator, organizes a dedication ceremony that presents the piece to the community and recognizes the artistic efforts of the artist.  This may occur consecutively with the dedication ceremony for the capital project or at a later date, if the artwork is completed after the capital improvement project.   For your convenience, an outline for coordinating a dedication ceremony is located in Appendix H.

# PART TWO
PRIVATELY FUNDED ART IN PUBLIC PLACES

An important source of public art is that which is privately funded, but located in a public place. Usually, such works are commissioned by an individual, a group of individuals, a non-profit organization or a business or corporation.  For some personal reason, a patron wishes to offer the City a piece of artwork, often as a memorial to a person or event.  Sometimes the patron can even be an artist who wishes to offer additional enhancement to the community and is able to find financial backers to support his or her endeavor.  Whatever may be the reason for the offer of public art to be placed on City property, the offer triggers the following process.

## Submittal Of A Proposal

1.	Submittal Form.  All proposals for privately funded public art placed on City property are submitted to the City's Public Art Coordinator on the appropriate form.  (Appendix I) The form must be accompanied by drawings, models, photographs or any other graphic depiction that will help to clearly define the artwork.  All proposals must be for original works of art. (See Introduction – What is Public Art?)

2.	Solicitation of Competitive Proposals.  When a proposal is submitted, whether by a patron or by an artist, it is not necessary for the City to solicit additional competitive proposals for the same location from other artists.

## Evaluation Of A Proposal

1.	Evaluation Jury.  Once the proposal is received by the Public Art Coordinator, s/he calls together a jury from a standing pool of resource individuals to judge the merits of the proposal.

a.	Jury Resource Pool.  The resource pool is made up of members who are reflective of various artistic disciplines, and include profit/non-profit business people, educators, historians, art patrons and individuals with engineering, architecture, landscape architecture and construction backgrounds who have indicated a desire to serve on a jury.

b.	Arts Council Assistance.  The San Luis Obispo County Arts Council is responsible for providing assistance in locating volunteers from the artistic disciplines to help create the pool.

2.	Jury Membership.  The jury consists of no less than five individuals whose background and interest are appropriate to the type and location of artwork being proposed.

a.	Artwork in Public Parks.  If the artwork is to be placed in a public park, a representative of the Parks and Recreation Commission is included on the jury.

b.	Artwork in Historical Location.  If the artwork is to be placed in a location of historical significance, a member of the Historical Society or another historian and a member of the Cultural Heritage Committee is included on the jury.

3.	Evaluation Criteria.  The jury applies the standard Guidelines for public art (Appendix C) in making a determination that the proposed project is acceptable to the City and should move forward in the approval process.

4.	Evaluation Criteria for Historical Locations.  Projects proposed for areas of high historical sensitivity, such as Mission Plaza and surrounding area, should be given the closest possible scrutiny to determine if the project would be an enhancement to the area.  Projects which do not garner the unanimous support of the jury will not proceed.

5.	Appeal Process.  If the jury rejects a proposal, the patron has the right to appeal this decision to the City Council in accordance with the appeals procedures in Section 1.20.020 of the Municipal Code.  The jury’s findings and rationale for rejecting the project will be made available to the Council when considering the appeal.

## Approval of a Proposal

1.	Approval Process.  Once a privately funded project is recommended for placement on City-owned property, it will be reviewed by the following departments and City advisory bodies.  The City's Public Art Coordinator acts as the project manager for all such projects and is responsible for "shepherding" them through the following approval stages.  It should be noted that, with the exception of the first step, this is the same approval process used for City-sponsored public art.  A more detailed explanation of this process can be found in Part One – Evaluating and Approving Public Art.

- The Public Art Coordinator reviews the proposed project to assure that it complies with the City's Donation Acceptance Policy.  (Appendix J).

- The Public Works Director or his designee(s) reviews the proposal to insure:

- that the artwork's placement will not create undue difficulties for maintenance of the surrounding area.

- that the proposed materials are durable and will not create significant maintenance problems for the artwork itself.

- that any engineering or structural concerns are addressed

- The Risk Manager and the Public Works Department reviews the proposal to assess whether or not it provides undue risks or safety issues.

- The Architectural Review Commission reviews the proposal to assure that it meets the adopted Guidelines for Public Art. (Appendix C)

- In some cases, proposals may take additional review because of their nature, design or location.

2.	Council Approval.  Ultimately, the City Council provides final approval of the proposal.

## Contract Preparation

Upon conceptual approval of the project by the City Council, the patron and the City sign a contract establishing the terms of the proposed installation of privately funded public art in public places.  The Council should be asked to delegate authority to sign the contract to the CAO as part of the conceptual approval process.  Appendix E contains a sample contract that should be adapted, as necessary, and used for this purpose.

## Issuing of Permits

The patron is directed to prepare plans and specifications for the artwork.  See Part One - Public Art Installations, for the process to be followed for permitting and installation of the public art project.

## Labeling of Artwork

1.	Standard Plaque.  In order to avoid the use of donated public art for advertising purposes, a standard plaque, approved by the City Council, is used for all labeling. The plaque contains:

- title of artwork

- artist's name

- patron's name

- date of completion

- material(s) used (optional)

- short explanation of work (optional)

2.	Deviation from Standard Plaque.  All requests to deviate from the standard plaque are made to the City Administrative Officer (CAO) or his designee.  Should the CAO or his designee deny the proposed deviation, the patron may appeal this decision to the City Council in accordance with the appeals procedures in Section 1.20.020 of the Municipal Code.

## Final Acceptance

1.	Maintenance.  Before accepting the project, the Public Art Coordinator provides the Public Works Department with a complete set of plans, specifications, attachments, fabrication details and a copy of the City's Public Art Maintenance Record Form (Appendix G). See Part One - Maintenance and Repair, for additional information.

2.	Inspection and Acceptance.  All donated projects on public property must have final inspection approval by the City's Building Division and by the Public Art Coordinator.  See Part One – Final Acceptance.

3.	Ownership.  Upon completion, the artwork becomes the property of the City.

## Dedication of Artwork

Once installation of the artwork is complete, the Public Art Coordinator organizes a dedication ceremony that presents the piece to the community and recognizes the artistic efforts of the artist.  An outline for coordinating a dedication ceremony is located in Appendix H.

# PART THREE
PUBLIC ART IN PRIVATE DEVELOPMENT

On August 15, 2000, the City Council passed an Ordinance Relating to Public Art in Private Development.  The ordinance is designed to further enhance the aesthetic environment of the City by requiring private property owners and developers to incorporate a piece(s) of art in new developments or substantially improved developments in the City, or voluntarily elect to purchase a piece of art and donate it to the City or pay a public art in-lieu fee.  (See Appendix K for enabling legislation.)  The Public Art in Private Development program is designed to allow the applicant some flexibility in meeting the requirements of the ordinance.

If the applicant chooses to incorporate a piece of public art into the project, s/he may choose to send out a Request for Proposals (RFP), a Request for Qualifications (RFQ), or purchase an already existing piece of art.  While this is the sole responsibility of the developer, the Community Development Department assists by informing the applicant of options and opportunities, providing a packet of resources (Appendix N), and the name and phone number for the Art Council’s Art in Public Places committee chair, who will guide the applicant through the RFP/RFQ process, if so desired.

The following sections provide details for processing public art in private development, including 1) placement of public art on private property, 2) accepting public art donated to the City by a private developer, and 3) payment of the art in-lieu fee.

## Placement of Public Art on Private Property

1.	Application Process

An application for placement of public art on private property is submitted to the Community Development Director and must include the following (see Appendix L, section 2):

- Preliminary sketches, photographs or other documentation of sufficient descriptive clarity to indicate the nature of the proposed public art, including an accurate description of the colors and materials to be used.

- An appraisal or other evidence of the value of the proposed public artwork, including acquisition and installation costs.

- A site plan clearly showing the location of the public art and its relation to pedestrian paths of travel on the site and in the vicinity, including adjacent rights-of-way.

- An elevation or perspective rendering showing the streetscape view of the public art, including the street elevations of adjacent properties.

- A narrative statement to demonstrate that the public art will be displayed in an area open and freely available to the general public, or that public accessibility will be provided in an equivalent manner based on the characteristics of the artwork or its placement on the site.

- Draft covenants, conditions and restrictions (CC&Rs) (see Appendix M), to be recorded with the County Recorder, which require the property owner, successor in interest, and assigns to:

- Maintain the public art in good condition as required by the City’s Guidelines for Public Art.

- Indemnify, defend and hold the City and related parties harmless from any and all claims or liabilities from the public art, in a form acceptable to the City Attorney.

- Maintain liability insurance, including coverage and limits as may be specified by the City’s Risk Manager.

2.   Approval for Placement of Public Art on Private Property

- The Community Development Director forwards the completed application to the Public Art Coordinator who convenes a public art jury to review the proposed art using the adopted Guidelines for public art and selection criteria.  (Appendix C)

- Upon recommendation of the public art jury, the public art application is forwarded to the Architectural Review Commission for review as to consistency with the Guidelines for public art.  (Appendix C)

- All approvals for placement of public art on private property will be obtained prior to issuance of a building permit.

## Public Art Donated to the City by a Private Developer

1.	Application Process

An application for public art donated to the City by a private developer is submitted to the Community Development Director and must include the following (see Appendix L, section 3):

- Preliminary sketches, photographs or other documentation of sufficient descriptive clarity to indicate the nature of the proposed public art, including an accurate description of the colors and materials to be used.

- An appraisal or other evidence of the value of the proposed public artwork, including acquisition and installation costs.

- A written agreement executed by or on behalf of the artist who created the public art that expressly waives his or her rights under the California Art Preservation Act or other applicable law. (See Appendix I)

2.	Approval of Public Art Donated to the City by a Private Developer

- Prior to the issuance of grading and building permits, the applicant presents the application for acceptance of public art donated to the City to the Community Development Director for review.

- The Community Development Director forwards the completed application to the Public Art Coordinator who then convenes a public art jury to review the proposed public art using adopted Guidelines and public art selection criteria.  (Appendix C)

- Upon recommendation of the public art jury, the public art application is forwarded to the Architectural Review Commission for review as to consistency with the adopted Guidelines for Public Art. (Appendix C)

- Upon the recommendation of the Architectural Review Commission, the application is forwarded to the City Council, which has the sole authority to accept, reject or conditionally accept the donation.

## Payment of Art In-Lieu Fee

If the payment of an art in-lieu fee is voluntarily elected, the minimum cost of the public art, including installation, is determined by the amount equal to one-half of one percent (.5%) of that portion of the total construction costs in excess of $100,000, not to exceed $50,000 for each building permit.  (See ordinance, Appendix K.)

## Certificate of Occupancy

1.	A Certificate of Occupancy requires full compliance with one of the following:

a. The approved public art has been placed on the site of the approved project, in a manner satisfactory to the Chief Building Official and the Public Art Coordinator.

- Donation of the approved public art has been accepted by the City Council.

- Public art in-lieu fees have been paid.

2.	If public art has been placed on the site of the approved project, the applicant must execute and record with the County Recorder covenants, conditions and restrictions (CC&Rs), which require the property owner to adhere to the following guidelines. (Appendix M)

a.  Maintain the public art in good condition as required by the City’s Public Art     Guidelines.

      - Defend and hold the City and related parties harmless from any and all claims or liabilities from the public art, in a form acceptable to the City Attorney.

      - Maintain liability insurance, including coverage and limits as may be specified by the City’s Risk Manager.

## Ownership of Public Art

            - All public art placed on the site of an applicant’s project remains the property of the applicant, as does the obligation to provide all maintenance necessary to preserve the public art in good condition.

            - Maintenance of public art includes preservation of the artwork in good condition to the satisfaction of the City, protection of the public art against physical defacement, mutilation or alteration and securing and maintaining fire and extended coverage of insurance and vandalism coverage in an amount to be determined by City’s Risk Manager.  Failure to maintain the public art will be declared to be a public nuisance.

            - If the owner fails to maintain the public art or fails to meet appropriate insurance requirements, upon reasonable notice, the City may perform all necessary repairs and maintenance or purchase insurance, and the associated costs become a lien against the real property.

            - All artwork donated to the City becomes the property and responsibility of the City upon acceptance by the City Council.

## Removal or Alteration of Public Art

- Public art installed on or integrated into a construction project can not be removed or altered without the approval of the City Council.

- If any public art provided on a development project is knowingly removed by the property owner without prior approval, the property owner will be required to contribute funds equal to the development project’s original public art requirement to the City’s Public Art In-Lieu account, or replace the removed artwork with one that is of comparable value and approved by the City Council. The City may, in addition, pursue any other available civil or criminal remedies or penalties.

## Use of the Public Art In-Lieu Funds

Per the Ordinance relating to public art in private development, in-lieu fees are deposited in an account maintained by the City Finance Director and may be used for acquisition, installation, and improvement of public art in the City.